## Data
Task ID | Task Name | Duration | Start | Resource | %Completion
1 | Scope | 4 | 2017-11-28 | Project Manager | 85%
2 | Analysis | 5 | 2017-12-03 | Analyst | 100%
3 | Software Requirements | 10 | 2017-12-08 | Analyst | 48.19%
4 | Design | 5 | 2017-12-21 | Architect | 100%
5 | Development | 21 | 2018-01-09 | Developer | 89.7%
6 | Functional testing | 15 | 2018-01-09 | Test | 100%
7 | E2E Testing | 10 | 2018-01-21 | Test | 68.86%
8 | Stablization | 7 | 2018-01-26 | Developer | 41.64%
9 | Training | 10 | 2018-02-09 | Tech Communicator | 0%
10 | Documentation | 10 | 2018-01-27 | Tech Communicator | 0%
11 | Pilot | 15 | 2018-02-19 | Project Manager | 0%
12 | Deployment | 5 | 2018-02-25 | Operations | 0%
13 | Post Implementation Review | 3 | 2018-03-06 | Project Manager | 0%